## Foglio1
TASKS	Start-date	Duration(gg)	Diego gaboardi	Giorgio giardini	Riccardo giol
RASD	16/10/2016	38	28	28	28
Meeting with clients	16/10/2016	1	1	1	1
Identification of stakeholders	17/10/2016	2	1	1	1
Definition of main Funtionalities	18/10/2016	7	6	3	5
Identification of requirements	20/10/2016	3	1	3	1
Meeting with local Authorities	22/10/2016	1	1	1	1
Identification of assumptions	23/10/2016	1	0	0	1
Definition of Use Case	24/10/2016	3	1	1	3
Costruction of basic activity diagrams	26/10/2016	4	3	2	2
Drawing of temporary mock-up	27/10/2016	3	1	1	1
Meeting with clients	01/11/2016	1	1	1	1
Definition of all Funtionalities	02/11/2016	5	1	3	1
Definition of final requirements	04/11/2016	4	1	1	3
Meeting with stakeholders	06/11/2016	1	1	1	1
Fixing of Use Case	08/11/2016	2	1	1	1
writing of all activity diagrams	10/11/2016	4	4	0	0
Drawing of final mock-up	14/11/2016	4	0	4	0
Scheduling	18/11/2016	2	0	0	2
First estimation of total cost	19/11/2016	1	1	1	0
Meeting with clients	20/11/2016	1	1	1	1
Final Refinements	21/11/2016	2	2	2	2
DD	23/11/2016	44	22	22	22
Definition of High-level architecture	23/11/2016	4	1	1	3
Identification of main components	25/11/2016	4	3	1	1
Deploying and runtime views	29/11/2016	3	1	1	1
Meeting with clients	02/12/2016	1	1	1	1
Definition of complete architecture	03/12/2016	5	1	1	4
Definition of all Components	06/12/2016	5	2	3	2
Definition of interfaces	09/12/2016	4	3	1	1
Identification of some critical Algorithms	13/12/2016	2	0	2	0
Meeting with clients	15/12/2016	1	1	1	1
Eventual change in the Architecture	16/12/2016	2	1	1	1
Eventual change in the Components	18/12/2016	2	1	1	1
identification of definitive interfaces	20/12/2016	3	2	2	1
Design of algorithms	27/12/2016	3	2	3	2
Meeting with Clients	03/01/2017	1	1	1	1
Final Refinements	04/01/2017	2	2	2	2
DEVELOPMENT	09/01/2017	325	321	321	321
Subcomponent development	09/01/2017	100	70	30	30
External component Analysis	01/02/2017	40	10	23	10
Code inspection	23/01/2017	100	25	55	25
Unit testing	10/02/2017	110	30	30	75
Subcomponent integration	15/05/2017	20	15	5	5
Component development	05/06/2017	60	15	40	15
Component Integration	27/06/2017	38	20	10	10
Integration testing	15/06/2017	50	15	15	30
System Testing	20/07/2017	30	20	20	20
Apps Development	25/08/2017	40	10	10	30
Apps integration	02/09/2017	30	8	20	8
Apps testing	09/09/2017	40	30	10	10
Internal Demostration	19/10/2017	5	4	4	4
Fixes	24/10/2017	15	15	15	15
Second Internal Demostration	02/11/2017	5	4	4	4
Demostration to Clients	10/11/2017	2	2	2	2
Demostration to Stakeholders	12/11/2017	2	2	2	2
Fixes	14/11/2017	5	5	5	5
Demostration to Clients	19/11/2017	2	2	2	2
Demostration to Stakeholders	21/11/2017	2	2	2	2
Final Fixes	23/11/2017	4	4	4	4
Documents revision	27/11/2017	3	3	3	3
User Manual	10/11/2017	20	10	10	10
DEPLOYMENT	01/12/2017	30	30	30	30
System Deployment	01/12/2017	30	30	30	30
Teaching meeting to amministrators	10/12/2017	3	3	3	3
Teaching meeting with Assistants	13/12/2017	3	3	3	3
Preparations	20/12/2017	10	10	10	10
START-UP	10/01/2018	21	21	21	21
System first start	10/01/2018	21	21	21	21
Real-Life Simulation	11/01/2018	20	20	20	20
Main updates and checks	10/01/2018	21	21	21	21

		42744,00