## Foglio1
TASKS | Start-date | Duration(gg) | Diego gaboardi | Giorgio giardini | Riccardo giol
RASD | 2016-10-16 | 38 | 28 | 28 | 28
Meeting with clients | 2016-10-16 | 1 | 1 | 1 | 1
Identification of stakeholders | 2016-10-17 | 2 | 1 | 1 | 1
Definition of main Funtionalities | 2016-10-18 | 7 | 6 | 3 | 5
Identification of requirements | 2016-10-20 | 3 | 1 | 3 | 1
Meeting with local Authorities | 2016-10-22 | 1 | 1 | 1 | 1
Identification of assumptions | 2016-10-23 | 1 | 0 | 0 | 1
Definition of Use Case | 2016-10-24 | 3 | 1 | 1 | 3
Costruction of basic activity diagrams | 2016-10-26 | 4 | 3 | 2 | 2
Drawing of temporary mock-up | 2016-10-27 | 3 | 1 | 1 | 1
Meeting with clients | 2016-11-01 | 1 | 1 | 1 | 1
Definition of all Funtionalities | 2016-11-02 | 5 | 1 | 3 | 1
Definition of final requirements | 2016-11-04 | 4 | 1 | 1 | 3
Meeting with stakeholders | 2016-11-06 | 1 | 1 | 1 | 1
Fixing of Use Case | 2016-11-08 | 2 | 1 | 1 | 1
writing of all activity diagrams | 2016-11-10 | 4 | 4 | 0 | 0
Drawing of final mock-up | 2016-11-14 | 4 | 0 | 4 | 0
Scheduling | 2016-11-18 | 2 | 0 | 0 | 2
First estimation of total cost | 2016-11-19 | 1 | 1 | 1 | 0
Meeting with clients | 2016-11-20 | 1 | 1 | 1 | 1
Final Refinements | 2016-11-21 | 2 | 2 | 2 | 2
DD | 2016-11-23 | 44 | 22 | 22 | 22
Definition of High-level architecture | 2016-11-23 | 4 | 1 | 1 | 3
Identification of main components | 2016-11-25 | 4 | 3 | 1 | 1
Deploying and runtime views | 2016-11-29 | 3 | 1 | 1 | 1
Meeting with clients | 2016-12-02 | 1 | 1 | 1 | 1
Definition of complete architecture | 2016-12-03 | 5 | 1 | 1 | 4
Definition of all Components | 2016-12-06 | 5 | 2 | 3 | 2
Definition of interfaces | 2016-12-09 | 4 | 3 | 1 | 1
Identification of some critical Algorithms | 2016-12-13 | 2 | 0 | 2 | 0
Meeting with clients | 2016-12-15 | 1 | 1 | 1 | 1
Eventual change in the Architecture | 2016-12-16 | 2 | 1 | 1 | 1
Eventual change in the Components | 2016-12-18 | 2 | 1 | 1 | 1
identification of definitive interfaces | 2016-12-20 | 3 | 2 | 2 | 1
Design of algorithms | 2016-12-27 | 3 | 2 | 3 | 2
Meeting with Clients | 2017-01-03 | 1 | 1 | 1 | 1
Final Refinements | 2017-01-04 | 2 | 2 | 2 | 2
DEVELOPMENT | 2017-01-09 | 325 | 321 | 321 | 321
Subcomponent development | 2017-01-09 | 100 | 70 | 30 | 30
External component Analysis | 2017-02-01 | 40 | 10 | 23 | 10
Code inspection | 2017-01-23 | 100 | 25 | 55 | 25
Unit testing | 2017-02-10 | 110 | 30 | 30 | 75
Subcomponent integration | 2017-05-15 | 20 | 15 | 5 | 5
Component development | 2017-06-05 | 60 | 15 | 40 | 15
Component Integration | 2017-06-27 | 38 | 20 | 10 | 10
Integration testing | 2017-06-15 | 50 | 15 | 15 | 30
System Testing | 2017-07-20 | 30 | 20 | 20 | 20
Apps Development | 2017-08-25 | 40 | 10 | 10 | 30
Apps integration | 2017-09-02 | 30 | 8 | 20 | 8
Apps testing | 2017-09-09 | 40 | 30 | 10 | 10
Internal Demostration | 2017-10-19 | 5 | 4 | 4 | 4
Fixes | 2017-10-24 | 15 | 15 | 15 | 15
Second Internal Demostration | 2017-11-02 | 5 | 4 | 4 | 4
Demostration to Clients | 2017-11-10 | 2 | 2 | 2 | 2
Demostration to Stakeholders | 2017-11-12 | 2 | 2 | 2 | 2
Fixes | 2017-11-14 | 5 | 5 | 5 | 5
Demostration to Clients | 2017-11-19 | 2 | 2 | 2 | 2
Demostration to Stakeholders | 2017-11-21 | 2 | 2 | 2 | 2
Final Fixes | 2017-11-23 | 4 | 4 | 4 | 4
Documents revision | 2017-11-27 | 3 | 3 | 3 | 3
User Manual | 2017-11-10 | 20 | 10 | 10 | 10
DEPLOYMENT | 2017-12-01 | 30 | 30 | 30 | 30
System Deployment | 2017-12-01 | 30 | 30 | 30 | 30
Teaching meeting to amministrators | 2017-12-10 | 3 | 3 | 3 | 3
Teaching meeting with Assistants | 2017-12-13 | 3 | 3 | 3 | 3
Preparations | 2017-12-20 | 10 | 10 | 10 | 10
START-UP | 2018-01-10 | 21 | 21 | 21 | 21
System first start | 2018-01-10 | 21 | 21 | 21 | 21
Real-Life Simulation | 2018-01-11 | 20 | 20 | 20 | 20
Main updates and checks | 2018-01-10 | 21 | 21 | 21 | 21
42744
Formulas:
Start-date = [Start-date, row above]+[Duration(gg), row above]
Start-date = [Start-date, row below]